## Details
Chapter | Ch.Name | Section | Sec.Name | Author | Early stages | Ready for review 1 | Review 1 completed | Ready for review 2 | Review 2 completed | Part of pilot | Finished | Stage
1 | Numbers and coordinate systems | 1 | Set theory and logic | [8 empty] | Not started
1 | Numbers and coordinate systems | 2 | Real numbers | W.M. Schouten-Straatman | Yes | [6 empty] | Early stages
1 | Numbers and coordinate systems | 3 | Complex numbers | W.M. Schouten-Straatman | Yes | Yes | Yes |  |  | EE1G1 - 2026-2027 Q1 |  | Review 1 completed
1 | Numbers and coordinate systems | 4 | Trigonometry | R. Koekoek | Yes | Yes | Yes | Yes |  |  |  | Ready for review 2
1 | Numbers and coordinate systems | 5 | Coordinate systems | R. Koekoek | Yes | [6 empty] | Early stages
1 | Numbers and coordinate systems | 6 | Polar form of complex numbers | W.M. Schouten-Straatman | Yes | Yes | Yes |  |  | EE1G1 - 2026-2027 Q1 |  | Review 1 completed
1 | Numbers and coordinate systems | 7 | Finite summations and multiplications | R. Koekoek | Yes | Yes | [5 empty] | Ready for review 1
2 | Vector algebra | 1 | Vectors | A.T. Hensbergen & N.D. Verhulst | Yes | Yes | Yes | Yes | Yes |  | Yes | Finished
2 | Vector algebra | 2 | Dot product | A.T. Hensbergen & N.D. Verhulst | Yes | Yes | Yes | Yes | Yes |  | Yes | Finished
2 | Vector algebra | 3 | Cross product | A.T. Hensbergen & N.D. Verhulst | Yes | Yes | Yes | Yes | Yes |  | Yes | Finished
2 | Vector algebra | 4 | Lines and planes | A.T. Hensbergen & N.D. Verhulst | Yes | Yes | Yes | Yes | Yes |  | Yes | Finished
2 | Vector algebra | 5 | Determinants | A.T. Hensbergen & N.D. Verhulst | Yes | Yes | Yes | Yes | Yes |  | Yes | Finished
3 | Functions and curves | 1 | Functions of one variable | W.M. Schouten-Straatman | Yes | Yes | Yes | Yes |  | EE1G1 - 2026-2027 Q1 |  | Ready for review 2
3 | Functions and curves | 2 | Properties of functions | W.M. Schouten-Straatman | Yes | Yes | Yes | Yes |  | EE1G1 - 2026-2027 Q1 |  | Ready for review 2
3 | Functions and curves | 3 | Curves in R^2 | W.M. Schouten-Straatman | Yes | Yes | Yes |  |  |  |  | Review 1 completed
3 | Functions and curves | 4 | Rational functions | D. den Ouden-van der Horst | Yes | Yes | Yes | Yes | Yes | EE1G1 - 2026-2027 Q1 | Yes | Finished
3 | Functions and curves | 5 | Inverse functions | W.M. Schouten-Straatman | Yes | Yes | Yes | Yes |  | EE1G1 - 2026-2027 Q1 |  | Ready for review 2
3 | Functions and curves | 6 | Nonlinear equations of one variable | [8 empty] | Not started
3 | Functions and curves | 7 | Limits at a point | W.M. Schouten-Straatman | Yes | Yes | Yes | Yes |  | EE1G1 - 2026-2027 Q1 |  | Ready for review 2
3 | Functions and curves | 8 | Limits at infinity | W.M. Schouten-Straatman | Yes | Yes | Yes | Yes |  | EE1G1 - 2026-2027 Q1 |  | Ready for review 2
3 | Functions and curves | 9 | Continuity | W.M. Schouten-Straatman | Yes | Yes | Yes | Yes | Yes | EE1G1 - 2026-2027 Q1 | Yes | Finished
4 | Differentiation | 1 | Differentiability | W.M. Schouten-Straatman | Yes | Yes | Yes |  |  | EE1G1 - 2026-2027 Q1 |  | Review 1 completed
4 | Differentiation | 2 | Chain rule | W.M. Schouten-Straatman | Yes | Yes | Yes | Yes |  | EE1G1 - 2026-2027 Q1 |  | Ready for review 2
4 | Differentiation | 3 | Product and quotient rule | W.M. Schouten-Straatman | Yes | Yes | Yes | Yes |  | EE1G1 - 2026-2027 Q1 |  | Ready for review 2
4 | Differentiation | 4 | Graphs and extreme values | W.M. Schouten-Straatman | Yes | Yes | Yes | Yes |  | EE1G1 - 2026-2027 Q1 |  | Ready for review 2
4 | Differentiation | 5 | Properties of graphs | W.M. Schouten-Straatman | Yes | [6 empty] | Early stages
4 | Differentiation | 6 | Slopes of curves in R^2 | W.M. Schouten-Straatman | Yes | Yes | Yes |  |  | EE1G1 - 2026-2027 Q1 |  | Review 1 completed
4 | Differentiation | 7 | Derivatives of inverse functions | W.M. Schouten-Straatman | Yes | Yes | Yes | Yes |  | EE1G1 - 2026-2027 Q1 |  | Ready for review 2
4 | Differentiation | 8 | Approximating functions | D. den Ouden-van der Horst | Yes | Yes | Yes | Yes |  |  |  | Ready for review 2
4 | Differentiation | 9 | l’Hospital’s rule | W.M. Schouten-Straatman | Yes | Yes | [5 empty] | Ready for review 1
5 | Integration | 1 | Definite integrals | R. Koekoek | Yes | Yes | Yes | Yes |  | EE1G1 - 2026-2027 Q1 |  | Ready for review 2
5 | Integration | 2 | Indefinite integrals | R. Koekoek | Yes | Yes | Yes | Yes |  | EE1G1 - 2026-2027 Q1 |  | Ready for review 2
5 | Integration | 3 | Fundamental theorem of calculus | R. Koekoek | Yes | Yes | Yes |  |  | EE1G1 - 2026-2027 Q1 |  | Review 1 completed
5 | Integration | 4 | Integration by substitution | R. Koekoek | Yes | Yes | Yes |  |  | EE1G1 - 2026-2027 Q1 |  | Review 1 completed
5 | Integration | 5 | Integration by parts | R. Koekoek | Yes | Yes | Yes |  |  | EE1G1 - 2026-2027 Q1 |  | Review 1 completed
5 | Integration | 6 | Integration of trigonometric functions | R. Koekoek | Yes | Yes | [5 empty] | Ready for review 1
5 | Integration | 7 | Integration of rational functions | R. Koekoek | Yes | Yes | [5 empty] | Ready for review 1
5 | Integration | 8 | Improper integrals | D. den Ouden-van der Horst | Yes | Yes | Yes |  |  |  |  | Review 1 completed
5 | Integration | 9 | Approximating integrals | D. den Ouden-van der Horst | Yes | Yes | [5 empty] | Ready for review 1
6 | Sequences | 1 | Sequences and their types | R. Koekoek | Yes | Yes |  |  |  | EE1M2 - 2026-2027 Q3 |  | Ready for review 1
6 | Sequences | 2 | Properties of sequences | R. Koekoek | Yes | Yes |  |  |  | EE1M2 - 2026-2027 Q3 |  | Ready for review 1
6 | Sequences | 3 | Convergence of sequences | R. Koekoek | Yes | Yes |  |  |  | EE1M2 - 2026-2027 Q3 |  | Ready for review 1
6 | Sequences | 4 | Iterative methods for various problems | [8 empty] | Not started
7 | Series | 1 | Series, sums and convergence | R. Koekoek | Yes | Yes |  |  |  | EE1M2 - 2026-2027 Q3 |  | Ready for review 1
7 | Series | 2 | Special types of series | R. Koekoek | Yes | Yes |  |  |  | EE1M2 - 2026-2027 Q3 |  | Ready for review 1
7 | Series | 3 | Tests for positive series | R. Koekoek | Yes | Yes |  |  |  | EE1M2 - 2026-2027 Q3 |  | Ready for review 1
7 | Series | 4 | Tests for general series | R. Koekoek | Yes | Yes |  |  |  | EE1M2 - 2026-2027 Q3 |  | Ready for review 1
7 | Series | 5 | Power series | R. Koekoek | Yes | Yes |  |  |  | EE1M2 - 2026-2027 Q3 |  | Ready for review 1
7 | Series | 6 | Taylor series | R. Koekoek | Yes | Yes |  |  |  | EE1M2 - 2026-2027 Q3 |  | Ready for review 1
7 | Series | 7 | Binomial series | R. Koekoek | Yes | Yes |  |  |  | EE1M2 - 2026-2027 Q3 |  | Ready for review 1
7 | Series | 8 | Fourier series | R. Koekoek | Yes | Yes | [5 empty] | Ready for review 1
7 | Series | 9 | The Riemann zeta function | R. Koekoek | Yes | Yes | [5 empty] | Ready for review 1
7 | Series | 10 | Catalan’s constant | R. Koekoek | Yes | Yes | [5 empty] | Ready for review 1
7 | Series | 11 | Generating functions | R. Koekoek | Yes | Yes | [5 empty] | Ready for review 1
8 | Functions, curves and surfaces | 1 | Functions of two or more variables | [8 empty] | Not started
8 | Functions, curves and surfaces | 2 | Properties of functions | [8 empty] | Not started
8 | Functions, curves and surfaces | 3 | Curves in R^3 | [8 empty] | Not started
8 | Functions, curves and surfaces | 4 | Surfaces in R^3 | [8 empty] | Not started
8 | Functions, curves and surfaces | 5 | Level curves and surfaces | [8 empty] | Not started
8 | Functions, curves and surfaces | 6 | Limits and continuity | [8 empty] | Not started
8 | Functions, curves and surfaces | 7 | Nonlinear systems in two variables | [8 empty] | Not started
9 | Partial differentiation | 1 | Partial derivatives | [8 empty] | Not started
9 | Partial differentiation | 2 | Directional derivative and gradient | [8 empty] | Not started
9 | Partial differentiation | 3 | Approximating functions and differentiability | [8 empty] | Not started
9 | Partial differentiation | 4 | Local extrema | [8 empty] | Not started
9 | Partial differentiation | 5 | Global extrema | [8 empty] | Not started
9 | Partial differentiation | 6 | Optimisation under equality constraints | [8 empty] | Not started
10 | Multivariable integration | 1 | Double integrals | R. Koekoek | Yes | [6 empty] | Early stages
10 | Multivariable integration | 2 | Coordinate transformations in R^2 | R. Koekoek | Yes | [6 empty] | Early stages
10 | Multivariable integration | 3 | Triple integrals | R. Koekoek | Yes | [6 empty] | Early stages
10 | Multivariable integration | 4 | Coordinate transformations in R^3 | R. Koekoek | Yes | [6 empty] | Early stages
10 | Multivariable integration | 5 | Multivariable integrals | [8 empty] | Not started
10 | Multivariable integration | 6 | Line integrals | [8 empty] | Not started
10 | Multivariable integration | 7 | Surface integrals | [8 empty] | Not started
11 | Vector calculus | 1 | Vector fields | [8 empty] | Not started
11 | Vector calculus | 2 | Line integrals of vector fields | [8 empty] | Not started
11 | Vector calculus | 3 | Fundamental theorem of line integrals | [8 empty] | Not started
11 | Vector calculus | 4 | Green’s theorem | [8 empty] | Not started
11 | Vector calculus | 5 | Surface integrals of vector fields | [8 empty] | Not started
11 | Vector calculus | 6 | Divergence and curl | [8 empty] | Not started
11 | Vector calculus | 7 | Gauß’ theorem | [8 empty] | Not started
11 | Vector calculus | 8 | Stokes’ theorem | [8 empty] | Not started
12 | Introduction to differential equations | 1 | Classifications and solutions | W.M. Schouten-Straatman | Yes | Yes | Yes | Yes |  | EE1G1 - 2026-2027 Q1 |  | Ready for review 2
12 | Introduction to differential equations | 2 | Existence and uniqueness of solutions | W.M. Schouten-Straatman | Yes | [6 empty] | Early stages
13 | First-order ordinary differential equations | 1 | Slope fields | W.M. Schouten-Straatman | Yes | Yes | Yes |  |  | EE1G1 - 2026-2027 Q1 |  | Review 1 completed
13 | First-order ordinary differential equations | 2 | First-order autonomous differential equations | W.M. Schouten-Straatman | Yes | [6 empty] | Early stages
13 | First-order ordinary differential equations | 3 | Separable differential equations | W.M. Schouten-Straatman | Yes | Yes | [5 empty] | Ready for review 1
13 | First-order ordinary differential equations | 4 | First-order linear differential equations | W.M. Schouten-Straatman | Yes | Yes | [5 empty] | Ready for review 1
13 | First-order ordinary differential equations | 5 | Exact differential equations | W.M. Schouten-Straatman | Yes | [6 empty] | Early stages
13 | First-order ordinary differential equations | 6 | Series solutions | W.M. Schouten-Straatman | Yes | [6 empty] | Early stages
13 | First-order ordinary differential equations | 7 | Approximating solutions | D. den Ouden-van der Horst | Yes | Yes | [5 empty] | Ready for review 1
14 | Second-order linear ordinary differential equations | 1 | Direction fields and solutions | [8 empty] | Not started
14 | Second-order linear ordinary differential equations | 2 | Homogeneous problems with constant coefficients | W.M. Schouten-Straatman | Yes | Yes | Yes |  |  | EE1G1 - 2026-2027 Q1 |  | Review 1 completed
14 | Second-order linear ordinary differential equations | 3 | Inhomogeneous problems with constant coefficients | W.M. Schouten-Straatman | Yes | [6 empty] | Early stages
14 | Second-order linear ordinary differential equations | 4 | Problems with nonconstant coefficients | [8 empty] | Not started
14 | Second-order linear ordinary differential equations | 5 | Series solutions | W.M. Schouten-Straatman | Yes | [6 empty] | Early stages